## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
1 | Allotments 1 | Blue pip over grown | RISK 2 | Pipe from pump overgrow, PPC to manage | 2021-09-28 | 2021-09-06
2 | Pavillion 1 | Hedges overgrown | RISK 2 | Hedges to be cut, PPc to manage | 2021-09-02 | 2021-08-30
3 | Playing field 1 | Goal removed and in grass, due tostoolball match? Advisory only | RISK 2 | VHM to monitor, expected to go back up Tuesday? | 2021-09-28 | 2021-09-13 | 2021-09-20
4 | Playing field 2 | Cracked manhole in Tennis club track | RISK 2 | Repair - PPC to manage | PPC | C/F
5 | Playing field 3 | Cricket shed, missing plank | RISK 2 | Cricket club to repair, Kelvin aware 10/5/21 | P.Morgan | 2021-05-10
6 | VH car park 1 | Parking bays | RISK 2 | Re mark - PPC to manage | PPC | C/F
7 | VH car park 2 | Pigeon droppings | RISK 3 | PPC to concider Pigeon guards, quotes obtained | N.SATCHELL & PPC | C/F
8 | VH car park 3 | Twigs/sticks from under solar pannels | RISK 3 | PPC to concider Pigeon guards, quotes obtained | N.SATCHELL & PPC | C/F
9 | VH car park 4 | Hedges in need of cutting | RISK 2 | Hedge to be cut, PPC to manage | 2021-07-26 | C/F
10 | VH car park 5 | Over hanging branched & brambles west border | RISK 3 | Cut back over hanging limbs - PPC to manage | PPC | C/F
11 | Green 1 | Several fallen trees | RISK 2 | PPC to manage | PPC | C/F
12 | Green 2 | Garden waste x 3 dumped in woods | RISK 2 | PPC to Manage | AG & RJ 6/9/21 | 2021-09-06
13 | Green 3 | Heavy rain, track flooded,Advisory | RISK 2 | Advisory, PPC to monitor | 2021-09-02 | 2021-08-09
14 | Green 4 | 2 loose bricks residents side | RISK 2 | VHM to Monitor | PPC | C/F
15 | Green 5 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | C/F
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Allotments
RISK ASSESSMENT - ALLOTMENTS SEPT 2021 | [5 empty] | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | ü | ü | ü | ü
| Litter, Rubbish and General Waste | ü | ü | ü | ü
| Obstructions | ü | û | û | û | Blue pipe over grown, Area needs strimming, Risk 3 | Allotments 1
Raised Beds | Edges Clearly Visible | ü | ü | ü | ü
Water Butts | Check for Hazards | ü | ü | ü | ü
Wooded Area | Uneven Ground | ü | ü | ü | ü
| Fallen Trees Branches | ü | ü | ü | ü
| Overhanging Branches | ü | ü | ü | ü
| Brambles / Nettles | ü | ü | ü | ü
| Litter, Rubbish and General Waste | ü | ü | ü | ü
| Wasp / Bee Nests | ü | ü | ü | ü
Stream | Warning Signs and Hazards | ü | ü | ü | ü
| Bank Hazards | ü | ü | ü | ü
| Flooding | ü | ü | ü | ü
Benches | Safe To Use | ü | ü | ü | ü
Gates | Good Order | ü | ü | ü | ü

## Playing Field
RISK ASSESSMENT - PLAYING FIELD SEPTEMBER 2021
Area | Items to Be Checked | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 |  | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | ü | ü | ü | ü
Litter On Field | Collect And Remove | ü | ü | ü | ü
Cricket Square | Tap | ü | ü | ü | ü
| General | ü | ü | ü | ü
Cricket Nets | General | ü | ü | ü | ü
Cricket Screen | Secured And Safe | ü | ü | ü | ü
Public Goals | Fit For Purpose | ü | ü | ü | ü
Club Goals | Posts / Nets | ü | û | ü | ü |  | 1 x Goal removed and lying in grass, presum due to stoolball match. Advise only | Playing field 1 | 2021-09-28 | 2021-09-20
Hedges / Trees | Overhanging Branches | ü | ü | ü | ü
Trees | Fallen Trees / Branches | ü | ü | ü | ü | ü
All Areas | Brambles / Nettles | ü | ü | ü | ü | ü
Litter / Hedges | Collect And Remove | ü | ü | ü | ü | ü
Hedges / Trees | Wasp And Bee Nests | ü | ü | ü | ü | ü
Pathways | Trip / Slip / Fall Hazards | ü | ü | ü | ü | ü
Tennis Track | Signage Visible | ü | ü | ü | ü | ü
| Detioration | û | û | û | û | û | Cracked manhole, | Playing field 2 | C/F
Benches x 2 | Fit For Purpose | ü | ü | ü | ü | ü
Bkt Ball Court | Tarmac Safe | ü | ü | ü | ü | ü
Litter Bins | Clear Overflowing Litter | ü | ü | ü | ü | ü
| Emptied On Schedule | ü | ü | ü | ü | ü
Outbuildings | Vandalism | ü | ü | ü | ü | ü
| Locked And Maintained | ü | û | û | û | û | Small plank rotten. Fallen off doesn’t effect security, KS aware 10/5/21, 2nd plank now off | Playing field 3 | 2021-06-01

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK SEPTEMBER 2021
Area | Items to Be Checked | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | ü | ü | ü | ü
| Footpath Clear / Safe | ü | ü | ü | ü
| Signage Visible | ü | ü | ü | ü
| Trip Hazards | ü | ü | ü | ü
| Free From Litter | ü | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü | ü
| Overhanging Branches | û | û | û | û | Hedges need cutting | Pav car park 1 | 2021-09-02
| Fallen Branches / Trees | ü | ü | ü | ü
| Bollards Safe | ü | ü | ü | ü
| Gates Safe And Locked, when not in use | ü | ü | ü | ü
| Recycling Compound | ü | ü | ü | ü

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK SEPTEMBER 2021
Area | Items to Be Checked | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | û | û | û | Many faded, Risk 2 | VH car park 1 | 2019-11-01
| Car Park Lighting | ü | ü | ü | ü
| Footpath Clear / Safe | û | û | û | û | Pigeon droppings | VH car park 2 | 2020-09-30
| Trip Hazards | û | û | û | û | Twigs/sticks from under solar pannels | VH car park 3 | 2020-09-30
| Hedges Safe | ü | ü | ü | ü | Hedges need cutting, PPC to manage | VH car park 4 | 2021-07-26
| Free From Litter | ü | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü | ü
| Overhanging Branches | û | û | û | û | Over hanging branches & brambles west border | VH car park 5 | 2021-01-07
| Fallen Trees / Branches | ü | ü | ü | ü
|  | ü | ü | ü | ü

## Green and Pond
RISK ASSESSMENT - GREEN AND POND SEPTEMBER 2021
Area | Items to Be Checked | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 |  | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | ü | ü | ü | ü
| Litter & Rubbish | ü | ü | ü | ü
| Manhole Cover | ü | ü | ü | ü
| Trees/Shrubs/Hedges | ü | ü | ü | ü
| Grass Length | ü | ü | ü | ü
| Spilt Rubbish By Bin | ü | ü | ü | ü
WOODS | Uneven Paths | ü | ü | ü | ü
| Overhanging Branches | ü | ü | ü | ü
| Fallen Trees / Branches | û | û | û | û |  |  | Several fallen trees, Risk 2 | Green 1 | 2021-01-06
| Brambles / Nettles | û | û | û | û |  |  | Garden waste x 3 dumpted in wooded area | Green 2 | 2021-09-06
| Dropped Litter/ Rubbish | ü | ü | ü | ü
| Wasps / Bee Nests | ü | ü | ü | ü
POND | Life Aid & Signage | ü | ü | ü | ü |  | Signs Missing
| Perimeter & Fence | ü | ü | ü | ü |  |  | Completed by contractor 23/8/21 | Green 3 | 2020-09-03 | 2021-08-23
| Trip/Slip/Fall Hazards | ü | ü | ü | ü |  |  | Heavy rain track flooded, advisory, Risk 2 | Green 4 | 2021-09-03
| Gully Edges | ü | ü | ü | ü
| Brick Wall | ü | ü | ü | ü |  |  | 2 loose bricks residents side, Risk 2 | Green 5 | 2020-09-03
| Wooden area | ü | ü | ü | ü
ü
Benches | Fit For Purpose | ü | ü | ü | ü | ü
ü
Bandstand | Electricity Supply Off/On | ü | ü | ü | ü | ü
| Electrics Undamaged | ü | ü | ü | ü
| Fit To Use | ü | ü | ü | ü | ü
| Path Safety | ü | ü | ü | ü | ü |  | Edge coming away, advisory, Risk 2 | Green 5 | 2020-09-03
ü
Bridge | Railings | ü | ü | ü | ü
| Base Of Bridge | ü | ü | ü | ü | ü
|  | ü | ü | ü | ü | ü
Benches | Safe To Use | ü | ü | ü | ü | ü