## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
2 | Playing field 1 | Cracked manhole in Tennis club track | RISK 2 | Repair - PC to manage, awaiting a quote from PM, Reminded before Xmas and again 34/1/23, Specialised contractor to assess. | PPC aware | C/F | PPC to arrange
| Playing field 2 | Club goals removed by need securing, stored | RISK 2 | PC to contact clubs and asked to secure or store, Junior Football goals removed, Seniors still need to be secured. | Week 1/5/23 PC aware | 04/05/2023 01/06/2023
| Playing field 3 | Astro turf run up to practice nets badly split | RISK 2 | Cricket aware | 01/06/2023, RJ
| Playing field 4 | Path round PAV crumbling, always had dips but deteriated over last month. | RISK 2 | Path ro be patched, PC to manage. | 04/07/2023. RJ AND AE
| Playing field 5 | 4 loose slabs outside electrical room | RISK 2-3 | Hazzard taped, Slabs to re-concreted, PC to manage | 2023-07-04
| Pavilion car park 1 | Recycling area, Clothing bin full, bags on floor | RISK 2 | HB informed 28/06/2023 | 2023-07-04
4 | VH car park 1 | Parking bays | RISK 2 | Re mark - PC to manage | PPC | C/F | CIL?
| VH car park 2 | Loose slab by bridge | RISK 2 | To be recermented - JB aware and hopes to fix | 2023-07-04
6 | Green 1 | Track flooded, not into Kimber cottages | RISK 2 | VHM to momitor, flooded due to heavy rain | 2022-02-28 | On going
8 | Green 2 | 2 loose bricks residents side | RISK 2 | VHM to monitor | PPC | On going
9 | Green 3 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | On going
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Allotments
RISK ASSESSMENT - ALLOTMENTS 2023 | [8 empty] | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-03 | 2023-06-01 | 2023-07-03 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | bar: 2023-01-03 to 2023-07-03
Litter, Rubbish and General Waste | bar: 2023-01-03 to 2023-07-03
Obstructions | bar: 2023-01-03 to 2023-07-03
Raised Beds | Edges Clearly Visible | bar: 2023-01-03 to 2023-07-03
Water Butts | Check for Hazards | bar: 2023-01-03 to 2023-07-03
Wooded Area | Uneven Ground | bar: 2023-01-03 to 2023-07-03
Fallen Trees Branches | bar: 2023-01-03 to 2023-07-03
Overhanging Branches | bar: 2023-01-03 to 2023-07-03
Brambles / Nettles | bar: 2023-01-03 to 2023-07-03
Litter, Rubbish and General Waste | bar: 2023-01-03 to 2023-07-03
Wasp / Bee Nests | bar: 2023-01-03 to 2023-07-03
Stream | Warning Signs and Hazards | bar: 2023-01-03 to 2023-07-03
Bank Hazards | bar: 2023-01-03 to 2023-07-03
Flooding | bar: 2023-01-03 to 2023-07-03
Benches | Safe To Use | bar: 2023-01-03 to 2023-07-03
ü
Gates | Good Order | bar: 2023-01-03 to 2023-07-03

## Playing Field
RISK ASSESSMENT - PLAYING FIELD 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-03 | 2023-06-01 | 2023-07-03 | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | bar: 2023-01-03 to 2023-07-03
Litter On Field | Collect And Remove | bar: 2023-01-03 to 2023-07-03
Cricket Square | Tap | bar: 2023-01-03 to 2023-07-03
General | bar: 2023-01-03 to 2023-07-03
Cricket Nets | General | [7 empty] | ASTRO TURF RUN UP SPLIT, KS AWARE | Playing field 3 | 2023-06-01 | bar: 2023-01-03 to 2023-07-03
Cricket Screen | Secured And Safe | bar: 2023-01-03 to 2023-07-03
Public Goals | Fit For Purpose | bar: 2023-01-03 to 2023-07-03
Club Goals | Posts / Nets | [7 empty] | GOALS REMOVED, BUT NEED SECURING | Playing field 2 | 2023-05-03 | bar: 2023-01-03 to 2023-07-03
Hedges / Trees | Overhanging Branches | bar: 2023-01-03 to 2023-07-03
Trees | Fallen Trees / Branches | bar: 2023-01-03 to 2023-07-03
All Areas | Brambles / Nettles | bar: 2023-01-03 to 2023-07-03
Litter / Hedges | Collect And Remove | bar: 2023-01-03 to 2023-07-03
Hedges / Trees | Wasp And Bee Nests | bar: 2023-01-03 to 2023-07-03
Pathways | Trip / Slip / Fall Hazards | [7 empty] | Path round PAV, is now crumbling, always had dips in it but deteriated over the last month. | Playing field 4 | 2023-07-04 | bar: 2023-01-03 to 2023-07-03
[9 empty] | 4 loose slabs outside electrical room, hazzard taped PPC aware, JB to look at. | Playing field 5 | 2023-07-04 | bar: 2023-04-04
Tennis Track | Signage Visible | bar: 2023-01-03 to 2023-07-03
| Detioration | [7 empty] | Cracked manhole, Specialised contractor to assess | Playing field 1 | C/F | bar: 2023-01-03 to 2023-07-03
ü
Benches x 2 | Fit For Purpose | bar: 2023-01-03 to 2023-07-03
ü
Bkt Ball Court | Tarmac Safe | bar: 2023-01-03 to 2023-07-03
ü
Litter Bins | Clear Overflowing Litter | bar: 2023-01-03 to 2023-07-03
Emptied On Schedule | bar: 2023-01-03 to 2023-07-03
[6 empty] | ü | ü | ü
Outbuildings | Vandalism | bar: 2023-01-03 to 2023-07-03
| Locked And Maintained | [7 empty] | PC managing, shed removed but cointents remain,removed, sand to be dispursed |  | 01/06/2021, June 2023 JB | Items removed, sand dispured | bar: 2023-01-03 to 2023-07-03

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-04 | 2023-06-01 | 2023-07-03 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | bar: 2023-01-03 to 2023-07-03
Footpath Clear / Safe | bar: 2023-01-03 to 2023-07-03
Signage Visible | bar: 2023-01-03 to 2023-07-03
Trip Hazards | bar: 2023-01-03 to 2023-07-03
Free From Litter | bar: 2023-01-03 to 2023-07-03
Litter Bin Maintained | bar: 2023-01-03 to 2023-07-03
Overhanging Branches | bar: 2023-01-03 to 2023-07-03
Fallen Branches / Trees | bar: 2023-01-03 to 2023-07-03
Bollards Safe | bar: 2023-01-03 to 2023-07-03
Gates Safe And Locked, when not in use | bar: 2023-01-03 to 2023-07-03
| Recycling Compound | [7 empty] | Bag of cloths left in compound, bank full. HB informed 28/6/2023 | Pavilion car park 1 | 2023-07-04 | bar: 2023-01-03 to 2023-07-03

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK 2023
Area | Items to Be Checked | 03/0102023 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 04/05/023 | 2023-06-01 | 2023-07-03 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | û | û | û | û | û | û | Many faded, Risk 2 | VH car park 1 | 2019-11-01
| Car Park Lighting | ü | ü | ü | ü | ü | ü | û | Loose slab by bridge | VH car park 2 | 2023-07-04
| Footpath Clear / Safe | ü | ü | ü | ü | ü | ü | ü
| Trip Hazards | ü | ü | ü | ü | ü | ü | ü
| Hedges Safe | ü | ü | ü | ü | ü | ü | ü
| Free From Litter | ü | ü | ü | ü | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü | ü | ü | ü | ü
| Overhanging Branches | û | û | û | ü | ü | ü | ü | Over hanging branches & brambles west border, cleared by working party |  | 2021-01-07 | 2023-03-18
| Fallen Trees / Branches | ü | ü | ü | ü | ü | ü | ü
|  | ü | ü | ü | ü | ü | ü | ü

## Green and Pond
RISK ASSESSMENT - GREEN AND POND 2023
Area | Items to Be Checked | 2023-01-03 | 2023-02-02 | 2023-03-02 | 2023-04-04 | 2023-05-04 | 2023-06-01 | 2023-07-03 | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | bar: 2023-01-03 to 2023-07-03
Litter & Rubbish | bar: 2023-01-03 to 2023-07-03
Manhole Cover | bar: 2023-01-03 to 2023-07-03
Trees/Shrubs/Hedges | bar: 2023-01-03 to 2023-07-03
Grass Length | bar: 2023-01-03 to 2023-07-03
Spilt Rubbish By Bin | bar: 2023-01-03 to 2023-07-03
WOODS | Uneven Paths | [8 empty] | Monitoring of track for flooding continued | GREEN 1 | 2022-02-28 | ON GOING | bar: 2023-01-03 to 2023-07-03
Overhanging Branches | bar: 2023-01-03 to 2023-07-03
Fallen Trees / Branches | bar: 2023-01-03 to 2023-07-03
Brambles / Nettles | bar: 2023-01-03 to 2023-07-03
Dropped Litter/ Rubbish | bar: 2023-01-03 to 2023-07-03
Wasps / Bee Nests | bar: 2023-01-03 to 2023-07-03
POND | Life Aid & Signage | [7 empty] | Signs Missing | Sign fallen off, reattached |  |  | 6/3/2023 JED | bar: 2023-01-03 to 2023-07-03
Perimeter & Fence | bar: 2023-01-03 to 2023-07-03
Trip/Slip/Fall Hazards | bar: 2023-01-03 to 2023-07-03
Gully Edges | bar: 2023-01-03 to 2023-07-03
| Brick Wall | [8 empty] | 2 loose bricks residents side, Risk 2 | GREEN 2 | 2020-09-03 | ON GOING | bar: 2023-01-03 to 2023-07-03
Wooden area | bar: 2023-01-03 to 2023-07-03
ü
Benches | Fit For Purpose | bar: 2023-01-03 to 2023-07-03
Bandstand | Electricity Supply Off/On | bar: 2023-01-03 to 2023-07-03
Electrics Undamaged | bar: 2023-01-03 to 2023-07-03
Fit To Use | bar: 2023-01-03 to 2023-07-03
| Path Safety | [8 empty] | Edge coming away, advisory, Risk 2 | GREEN 3 | 2020-09-03 | ON GOING | bar: 2023-01-03 to 2023-07-03
Bridge | Railings | bar: 2023-01-03 to 2023-07-03
Base Of Bridge | bar: 2023-01-03 to 2023-07-03
|  | ü | ü | ü | ü | ü | ü | ü
Benches | Safe To Use | bar: 2023-01-03 to 2023-07-03