## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
| Playing field 1 | PPC shed resting on concerte blocks | RISK 2 | PPC aware, JB to arrange a permiment fix | 2023-09-05 | 2023-09-18
| Playing field 2 | Astro turf run up to practice nets badly split | RISK 2 | Cricket aware, cricket to repair | 01/06/2023, RJ
| Playing field 3 | Path round PAV crumbling, always had dips but deteriated over last month. | RISK 2 | Path to be patched, PC to manage. | 04/07/2023. RJ AND AE
| Playing field 4 | 4 loose slabs outside electrical room | RISK 2-3 | Hazzard taped, Slabs to re-concreted, PC to manage | 2023-07-04
4 | VH car park 1 | Parking bays | RISK 2 | Re mark - PC to manage | PPC | C/F | CIL?
| VH car park 2 | Loose slab by bridge | RISK 2 | To be recermented - JB aware and hopes to fix | 2023-07-04
6 | Green 1 | TRACKS AROUND POND | RISK 3 | Track behind Kimber cottages floods in heavy rain, track behind pond extreamly muddy and slippery, VHM to monitor | 28/02/2022, 06/12/2023, 03/01/2024 | On going
9 | Green 2 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | On going
| Green 3 | Pond edge exposed since rushes have been removed | RISK 3 | PPC. EXTRA DEEP WATER SIGNES ORDERED, LIFE BUOY TO BE ORDERED IN SPRING 2024 | 05/09/2023, 5/12/2023 | On going
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Allotments
RISK ASSESSMENT - ALLOTMENTS 2023 |  |  | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2024-01-03 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | ü
| Litter, Rubbish and General Waste | ü
| Obstructions | ü
Raised Beds | Edges Clearly Visible | ü
Water Butts | Check for Hazards | ü
Wooded Area | Uneven Ground | ü
| Fallen Trees Branches | ü
| Overhanging Branches | ü
| Brambles / Nettles | ü
| Litter, Rubbish and General Waste | ü
| Wasp / Bee Nests | ü
Stream | Warning Signs and Hazards | ü
| Bank Hazards | ü
| Flooding | ü
Benches | Safe To Use | ü
Gates | Good Order | ü

## Playing Field
RISK ASSESSMENT - PLAYING FIELD 2023
Area | Items to Be Checked | 2024-01-03 | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | û | PPC SHED RESTING ON CONCRETE BLOCKS | Playing field 1 | 2023-09-18
Litter On Field | Collect And Remove | ü |  |  | 2023-10-04 | 2023-12-07
Cricket Square | Tap | ü
| General | ü
Cricket Nets | General | û | ASTRO TURF RUN UP SPLIT, KS AWARE | Playing field 2 | 2023-06-01
Cricket Screen | Secured And Safe | ü
Public Goals | Fit For Purpose | ü
Club Goals | Posts / Nets | ü
Hedges / Trees | Overhanging Branches | ü
Trees | Fallen Trees / Branches | ü
All Areas | Brambles / Nettles | ü
Litter / Hedges | Collect And Remove | ü
Hedges / Trees | Wasp And Bee Nests | ü
Pathways | Trip / Slip / Fall Hazards | û | Path round PAV, is now crumbling, always had dips in it but deteriated over the last month. | Playing field 3 | 2023-07-04
|  |  | 4 loose slabs outside electrical room, hazzard taped PPC aware, JB to look at. | Playing field 4 | 2023-07-04
Tennis Track | Signage Visible | ü
| Detioration | ü
Passing bays in good order, installed 4/10/2023
Benches x 2 | Fit For Purpose | ü
Bkt Ball Court | Tarmac Safe | ü
Litter Bins | Clear Overflowing Litter | ü
| Emptied On Schedule | ü
Outbuildings | Vandalism | ü

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK 2023
Area | Items to Be Checked | 2023-01-03 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | ü
| Footpath Clear / Safe | ü
| Signage Visible | ü
| Trip Hazards | ü
| Free From Litter | ü
| Litter Bin Maintained | ü
| Overhanging Branches | ü
| Fallen Branches / Trees | ü
| Bollards Safe | ü
| Gates Safe And Locked, when not in use | ü
| Recycling Compound | ü

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK 2023
Area | Items to Be Checked | 2024-01-03 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | Many faded, Risk 2 | VH car park 1 | 2019-11-01
| Car Park Lighting | ü |  |  | 2023-07-04
| Footpath Clear / Safe | ü
| Trip Hazards | û | loose slab by bridge, Risk 2 | VH car park 2
| Hedges Safe | ü
| Free From Litter | ü
| Litter Bin Maintained | ü
| Overhanging Branches | ü
| Fallen Trees / Branches | ü
ü

## Green and Pond
RISK ASSESSMENT - GREEN AND POND 2023
Area | Items to Be Checked | 2023-01-03 | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | ü
| Litter & Rubbish | ü
| Manhole Cover | ü
| Trees/Shrubs/Hedges | ü
| Grass Length | ü
| Spilt Rubbish By Bin | ü
WOODS | Uneven Paths/tracks | û |  | Monitoring of track for flooding continued, track behind pond extramly muddy and slippery | GREEN 1 | 2022-02-28 | ON GOING
| Overhanging Branches | ü
| Fallen Trees / Branches | ü
| Brambles / Nettles | ü
| Dropped Litter/ Rubbish | ü
| Wasps / Bee Nests | ü
POND | Life Aid & Signage | ü | Signs Missing
| Perimeter & Fence | ü |  | Additional deep water signs purchased, bouy to be ordered in spring | GREEN 2 | 2023-09-05
| Trip/Slip/Fall Hazards | ü
| Gully Edges | ü
| Brick Wall | ü
| Wooden area | ü
Benches | Fit For Purpose | ü
Bandstand | Electricity Supply Off/On | ü
| Electrics Undamaged | ü
| Fit To Use | ü
| Path Safety | û |  | Edge coming away, advisory, Risk 2 | GREEN 3 | 2020-09-03 | ON GOING
Bridge | Railings | ü
| Base Of Bridge | ü
ü
Benches | Safe To Use | ü