## PROBLEMS AND RISK PRIORITY
Item Number | Unique ID | Problem | Priority | Proposed Action | PC informed | Date | Date resolved
| Playing field 1 | PPC shed resting on concerte blocks | RISK 2 | PPC aware, JB to arrange a permiment fix | 2023-09-05 | 2023-09-18
| Playing field 2 | Astro turf run up to practice nets badly split | RISK 2 | Cricket aware, cricket have started to replace. Next work part March 2024 | 01/06/2023, RJ
| Playing field 3 | Path round PAV crumbling, always had dips but deteriated over last month. | RISK 2 | Path to be patched, PC to manage. | 04/07/2023. RJ AND AE
| Playing field 4 | 4 loose slabs outside electrical room | RISK 2-3 | Hazzard taped, Slabs to re-concreted, PC to manage | 2023-07-04
| Playing field 5 | Deep tyre tracks on field, new tyre tracks 2/3/24 | Risk 2/3 | Paul Manville to recitfy,VHM to monitor. New tyre tracks, photos sent to AE 4/3/2024 | 29/01/2024,AE 04/03/2024 | 2024-02-01
4 | VH car park 1 | Parking bays | RISK 2 | Re mark - PC to manage | PPC | C/F | CIL?
| VH car park 2 | Loose slab by bridge | RISK 2 | To be recermented - JB aware and hopes to fix | 2023-07-04
6 | Green 1 | TRACKS AROUND POND | RISK 3 | Track behind Kimber cottages floods in heavy rain, track behind pond extreamly muddy and slippery, VHM to monitor | 28/02/2022, 06/12/2023, 03/01/2024 | On going
9 | Green 2 | Edge coming away, advisory | RISK 2 | VHM to monitor | N.SATCHELL & PPC | On going
| Green 3 | Pond edge exposed since rushes have been removed | RISK 3 | PPC. EXTRA DEEP WATER SIGNES ORDERED, LIFE BUOY TO BE ORDERED IN SPRING 2024 | 05/09/2023, 5/12/2023 | On going
| Green 4 | low hanging branches along footpath in West Gate | RISK 3 | Branches need removing, risk of hitting head | 2024-02-02
| C/F = | ITEMS CARRIED FORWARD FOR OLD STYLE RA'S, PRE APRIL 2021
| RISK 1 | IMMPOBABLE
| RISK 2 | REMOTE
| RISK 3 | OCCASSIONAL (ACTION WITHIN 6 MONTHS)
| RISK 4 | PROBABLE (ACTION WITHIN 3 MONTHS)
| RISK 5 | HIGH RISK (IMMEDIATE ACTION)

## Notice boards
PPC notice boards, Checks for damage and deteriation
| JAN | FEB | MAR | APR | JUN | JUL | AUG | SET | SEPT | OCT | NOV | DEC | COMMENTS
| 2024-01-11 | 2024-02-01 | 2024-03-01
1/2 Moon | bar: JAN to MAR
Playing field, Skate park | bar: JAN to MAR
Playing field, carpark enterance | bar: JAN to MAR
Shop | [12 empty] | KEY HELD AT SHOP | bar: JAN to MAR
Green, West Gate | bar: JAN to MAR
Plough | bar: JAN to MAR
CHECKED BY | JAN: JED; FEB: JED; MAR: JED
Notivr board, Playing field, car park enterance worn and old

## Allotments
RISK ASSESSMENT - ALLOTMENTS 2023 |  |  |  |  | SUGGESTED EXAMPLES
Area | Items to Be Checked | 2024-01-03 | 2024-02-01 | 2024-03-04 | Issue | Item Number | Date Notified | Date Resolved
Main Footpaths | Hidden Potholes | ü | ü | ü
| Litter, Rubbish and General Waste | ü | ü | ü
| Obstructions | ü | ü | ü
Raised Beds | Edges Clearly Visible | ü | ü | ü
ü
Water Butts | Check for Hazards | ü | ü | ü
Wooded Area | Uneven Ground | ü | ü | ü
| Fallen Trees Branches | ü | ü | ü
| Overhanging Branches | ü | ü | ü
| Brambles / Nettles | ü | ü | ü
| Litter, Rubbish and General Waste | ü | ü | ü
| Wasp / Bee Nests | ü | ü | ü
Stream | Warning Signs and Hazards | ü | ü | ü
| Bank Hazards | ü | ü | ü
| Flooding | ü | ü | ü
Benches | Safe To Use | ü | ü | ü
Gates | Good Order | ü | ü | ü

## Playing Field
RISK ASSESSMENT - PLAYING FIELD 2023
Area | Items to Be Checked | 2024-01-03 | 2024-02-01 | 2024-03-04 | Issue | Item number | Date Notified | Date Resolved
Field | Trips / Slip Hazard | û | û | û | PPC SHED RESTING ON CONCRETE BLOCKS | Playing field 1 | 2023-09-18
Litter On Field | Collect And Remove | ü | ü | ü
Cricket Square | Tap | ü | ü | ü
| General | ü | ü | ü
Cricket Nets | General | û | û | û | ASTRO TURF RUN UP SPLIT, KS AWARE, 25th FEB WORKS TO REPLACE HAVE STARTED. | Playing field 2 | 01/06/2023 04/03/2024
Cricket Screen | Secured And Safe | ü | ü | ü
Public Goals | Fit For Purpose | ü | ü | ü
Club Goals | Posts / Nets | ü | ü | ü
Hedges / Trees | Overhanging Branches | ü | ü | ü
Trees | Fallen Trees / Branches | ü | ü | ü
All Areas | Brambles / Nettles | ü | ü | ü
Litter / Hedges | Collect And Remove | ü | ü | ü
Hedges / Trees | Wasp And Bee Nests | ü | ü | ü
Pathways | Trip / Slip / Fall Hazards | û | û | û | Path round PAV, is now crumbling, always had dips in it but deteriated over the last month. | Playing field 3 | 2023-07-04
[5 empty] | 4 loose slabs outside electrical room, hazzard taped PPC aware, JB to look at. | Playing field 4 | 2023-07-04
Tennis Track | Signage Visible | ü | ü | ü
| Detioration | ü | ü | ü
Passing bays in good order, installed 4/10/2023
Benches x 2 | Fit For Purpose | ü | ü | ü
Bkt Ball Court | Tarmac Safe | ü | ü | ü
Litter Bins | Clear Overflowing Litter | ü | ü | ü
| Emptied On Schedule | ü | ü | ü
Outbuildings | Vandalism | ü | ü | ü
Other | Tyre tracking on field |  | û | û | Tyre tracks on field, made by senior football, PM to rectify when dry enough and make sure that people are aware not to drive onto the field. New tyre tracks 01/03/24 photos sent to AE | Playing field 5 | AE aware Monday 29/01/2024 & Monday 04/03/24

## Pavilion Car Park
RISK ASSESSMENT - PAVILION CAR PARK 2023
Area | Items to Be Checked | 2023-01-03 | 2024-02-01 | 2024-03-04 | Issue | Item Number | Date Notified | Date Resolved
Car Park | Car Park Lighting | ü | ü | ü
| Footpath Clear / Safe | ü | ü | ü
| Signage Visible | ü | ü | ü
| Trip Hazards | ü | ü | ü
| Free From Litter | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü
| Overhanging Branches | ü | ü | ü
| Fallen Branches / Trees | ü | ü | ü
| Bollards Safe | ü | ü | ü
| Gates Safe And Locked, when not in use | ü | ü | ü
| Recycling Compound | ü | ü | ü

## Village Hall Car Park
RISK ASSESSMENT - VILLAGE HALL CAR PARK 2023
Area | Items to Be Checked | 2024-01-03 | 2024-02-01 | 2024-03-04 | Issue | Item number | Date Notified | Date Resolved
Car Park | Bay Marking | û | û | û | Many faded, Risk 2 | VH car park 1 | 2019-11-01
| Car Park Lighting | ü | ü | ü |  |  | 2023-07-04
| Footpath Clear / Safe | ü | ü | ü
| Trip Hazards | û | û | û | loose slab by bridge, Risk 2 | VH car park 2
| Hedges Safe | ü | ü | ü
| Free From Litter | ü | ü | ü
| Litter Bin Maintained | ü | ü | ü
| Overhanging Branches | ü | ü | ü
| Fallen Trees / Branches | ü | ü | ü
|  | ü | ü | ü

## Green and Pond
RISK ASSESSMENT - GREEN AND POND 2023
Area | Items to Be Checked | 2023-01-03 | 2024-02-01 | 2024-03-04 | Issue | Issue | Item Number | Date Notified | Date Resolved
GREEN | Hidden Potholes | ü | ü | ü
| Litter & Rubbish | ü | ü | ü
| Manhole Cover | ü | ü | ü
| Trees/Shrubs/Hedges | ü | ü | ü
| Grass Length | ü | û | û |  | low hanging branches along the footpath, need cutting back | GREEN 4 | 2024-02-02
| Spilt Rubbish By Bin | ü | ü | ü
WOODS | Uneven Paths/tracks | û | û | û |  | Monitoring of track for flooding continued, track behind pond extramly muddy and slippery | GREEN 1 | 2022-02-28 | ON GOING
| Overhanging Branches | ü | ü | ü
| Fallen Trees / Branches | ü | ü | ü
| Brambles / Nettles | ü | ü | ü
| Dropped Litter/ Rubbish | ü | ü | ü
| Wasps / Bee Nests | ü | ü | ü
POND | Life Aid & Signage | ü | ü | ü | Signs Missing
| Perimeter & Fence | ü | ü | ü |  | Additional deep water signs purchased, bouy to be ordered in spring | GREEN 2 | 2023-09-05
| Trip/Slip/Fall Hazards | ü | ü | ü
| Gully Edges | ü | ü | ü
| Brick Wall | ü | ü | ü
| Wooden area | ü | ü | ü
Benches | Fit For Purpose | ü | ü | ü
Bandstand | Electricity Supply Off/On | ü | ü | ü
| Electrics Undamaged | ü | ü | ü
| Fit To Use | ü | ü | ü
| Path Safety | û | û | û |  | Edge coming away, advisory, Risk 2 | GREEN 3 | 2020-09-03 | ON GOING
Bridge | Railings | ü | ü | ü
| Base Of Bridge | ü | ü | ü
|  | ü | ü | ü
Benches | Safe To Use | ü | ü | ü